## Sheet1
Status | day est | State | State Date | Project | Priority | Start Quarter | Due Date | Label | Action Lead | Back Up | Category | Short Description (see GitHub for details) | Update Date | Update Description | GitHub Issue
Done |  | 100% | 2019-10-27 | PHP Library - readme example | High |  |  | RPC Clients - Q419 Grant | Mitchell |  | Community Project | Create an organized readme example to standardize overview documentation and examples presentation
OVERDUE | 0 | 99% | 2019-10-30 | PHP Client Library | High | Q3-19 | 2019-11-02 | RPC Client | Ftechiz | Jason | Grant Round Q419 | PHP JSON-RPC Client Library for Factom
OVERDUE | 0 | 99% | 2019-10-27 | Ruby Client Library | High | Q3-19 | 2019-11-02 | RPC Client | Ftechiz | Jason | Grant Round Q419 | Ruby JSON-RPC Client Library for Factom
Done | 0 | 100% | 2019-11-03 | Haskell Client Library | High |  | 2019-11-01 | RPC Client | Sergey |  | Grant Round Q419 | Rust JSON-RPC Client Library for Factom
OVERDUE | 0 | 99% | 2019-11-02 | Swift Client Library | High | Q3-19 | 2019-11-02 | RPC Client | Ftechiz | Jason | Grant Round Q419 | Swift JSON-RPC Client Library for Factom
In Progress |  | 95% | 2019-11-03 | Company Email | Medium | Q4-19 |  | Corporate Matters | Jason |  | Kompendium Project | Email: member@kompendium.co
Done |  | 100% | 2019-10-27 | High Efficiency PEG Miner - R&D | High |  |  | PEG Mining Pool | Mitchell |  | Kompendium Project | Algorithm in Rust/Haskell, research API and Hosting Requirements & Options
To Do |  | 0% | 2019-10-27 | PEG/FCT/FAT Wallet - Mobile | High | Q4-19 |  | Wallet | Kelecorix | Sergey | Grant Round Q419 | Tasset iOS and Android PEG/FCT wallet
To Do |  | 0% | 2019-11-03 | R&D - Native ZKP atop of Factom Network | Medium | Q4-19 |  | ZKP | Kelecorix | Sergey | Community Project | Looking at DIZK-like system where ZKP implemented as a layer atop of Factom network and it uses nodes of Factom by corralling them into a synthetic cluster as workers to distribute compute requirements across network as a single large computer. Q4-19 R&D; Q1-20 Implement; Q2-20 Implement
To Do |  | 0% | 2019-10-27 | High Efficiency PEG Miner (Rust) | High | Q4-19 |  | PEG Mining Pool | Mitchell | Sergey | Kompendium Project | Server Side Mining Pool Software
Done |  | 100% | 2019-10-27 | Grant Proposal 1 | High |  | 2019-11-03 | RPC Client Collection - Back Pay | Jason | Sergey | Grant Round Q419 | (Back Pay) Grant For RPC Client Collection - Back Pay
Done |  | 100% | 2019-10-27 | Grant Proposal 2 | High |  | 2019-11-03 | Open API Client Back Pay | Jason | Sergey | Grant Round Q419 | (Back Pay) Grant For Open API Client Back Pay
Done |  | 100% | 2019-10-27 | Grant Proposal 3 | High |  | 2019-11-03 | PegNet Mobile Wallets | Jason | Sergey | Grant Round Q419 | Grant For PegNet Mobile Wallets
Done |  | 100% | 2019-10-27 | Grant Proposal 4 | High |  | 2019-11-03 | ? | Jason |  | Grant Round Q419
Done |  | 100% | 2019-11-03 | OPEN API Documentation | High |  |  | Open API | Sergey |  | Grant Round Q419 | Open API Client Documentation in support of library
Done |  | 100% | 2019-11-03 | Host OPEN API Server? | Low |  |  | Open API | Sergey | Jason | Community Project | Do we run the Haskell Open API as a server?
OVERDUE | 0 | 95% | 2019-10-27 | Rust Client Library | High | Q3-19 | 2019-10-31 | RPC Client | Mitchell |  | Grant Round Q319 | (FUNDED GRANT) Rust JSON-RPC Client Library for Factom
Done |  | 100% | 2019-11-03 | Swagger Instructions | High |  | 2019-11-02 | Open API | Sergey |  | Grant Round Q419 | Open API Client Documentation in support to library
To Do |  | 0% | 2019-10-27 | WASM add to Rust Client Library | High | Q4-19 |  | RPC Client | Mitchell | Sergey | Kompendium Project | Add WASM implementation to Rust Client Library
In Progress |  | 80% | 2019-11-03 | Private File Sharing | Low | Q4-19 |  | System Adminstration | Mitchell |  | Kompendium Project | Implement NextCloud as a File Exchange Service off of files.kompendium.co
Done |  | 100% | 2019-11-03 | Swagger File - pure script | High |  | 2019-11-02 | Open API | Sergey |  | Grant Round Q419 | Open API Client File for generation of library
Done |  | 100% | 2019-11-03 | Swagger File - pure script & instructions | High |  | 2019-11-02 | Open API | Sergey |  | Grant Round Q419 | Open API Client Documentation in support to library
To Do |  | 0% | 2019-10-27 | WASM Project | Low | Q4-19 |  | Alt PEG Miners | Mitchell | Sergey | Kompendium Project | WASM Project that adds value & PoC of Rust/WASM Client
To Do |  | 0% | 2019-10-27 | Evident App Project (Mobile) | Medium | Q4-19 |  | Evident | Mitchell |  | Kompendium Project | data/file Notary capabilities
Done |  | 100% | 2019-11-03 | Swagger File - Elm | High |  | 2019-11-02 | Open API | Sergey |  | Grant Round Q419 | Open API Client File for generation of library
Done |  | 100% | 2019-11-03 | Swagger File - Elm & instructions | High |  | 2019-11-02 | Open API | Sergey |  | Grant Round Q419 | Open API Client Documentation in support to library
To Do |  | 0% | 2019-11-03 | Kommunity - R&D / Design | Medium | Q4-19 | 2020-02-28 | Kommunity | Mitchell |  |  | Designing the system and protocol
To Do |  | 0% | 2019-11-03 | PoC: Build Factom-Etherium Bridge | Medium | Q4-19 |  | Kommunity | Mitchell | Ftechiz |  | PoC to connect ETH to FCT iso Kommunity: May consider inviting Sam and Alex to support Q4-19 R&D and PoC - Once Built: Q1-20 Ftechiz will build out additional bridges to EOS, TRX, ADA, Cosmos, ChainLink, IOTA.
To Do |  | 0% | 2019-11-03 | Enhanced IDE Design and R&D | High | Q4-19 |  | Katalyst | Sergey |  | Community Project | Enhanced IDE for Dapp/SC development: Q4-19 R&D; Q1-20 Build; Q2-20 Build
To Do |  | 0% | 2019-10-27 | Kartography | Low | Q2-20 |  | Kartography | Jason |  | Kompendium Project | Factom/FAT & maybe PEG leverage Minecraft Mod for DRM
To Do |  | 0% | 2019-10-27 | PEG Wallet - Desktop - R&D | Medium | Q1-20 |  | Wallet | Kelecorix | Sergey | Community Project | Tasset implemented as a desktop wallet
To Do |  | 0% | 2019-10-27 | PEG Wallet - Web-Wallet - R&D | Medium | Q1-20 |  | Wallet | Kelecorix | Sergey | Community Project | Tasset implemented as a desktop wallet
To Do |  | 0% | 2019-10-27 | Update Haskell Open Api based on whole OPEN API | High | Q4-19 | 2020-02-28 | Open API | Sergey |  | Community Project | Update Haskell Open API Server/Client to Full Open API
To Do |  | 0% | 2019-10-27 | ZKP/Bulletproofs Implementation | High | Q4-19 |  | ZKP | Sergey | Jason | Community Project | DIZK as a zkp PoC and functionality for Factom
To Do |  | 0% | 2019-11-03 | DApp Tool Suite - Better Truffle Suite R&D | Low | Q4-19 |  | Katalyst | Sergey |  | Community Project | IDE Complementary Dapp Dev Tool Suite - Like Truffle but better; Q4-19 R&D; Q1-20 R&D; Q2-20 Build; Q3-20 Build
To Do |  | 0% | 2019-10-27 | Haskell rpc client library - debug API | Low | Q4-19 | 2020-02-28 | RPC Client | Sergey |  | Grant Round Q419 | Finish Haskell rpc library by adding debug api
To Do |  | 0% | 2019-10-27 | Other Swagger files for library? | Low | Q4-19 | 2020-02-28 | Open API | Sergey |  | Grant Round Q419 | Open API Client & Documentation
To Do |  | 0% | 2019-10-27 | SC Implementation | Low | Q4-19 |  | Smart Contracts | Sergey | Kelecorix | Community Project | Making SC actually work on FAT
In Progress |  | 0% | 2019-10-27 | SC Paper - R&D | Low | Q4-19 | 2019-11-25 | Smart Contracts | Sergey | Jason | Community Project | Paper examining SC implementations across a variety of projects
To Do |  |  |  | R&D - Privileged, Private Enterprise BaaS | Low | Q2-20 |  | Konfidant | Kelecorix |  | Kompendium Project | BaaS - Privileged, Private Enterprise Solutions - leveraging ZKP layer, anchors data in the public Factom blockchain
To Do |  | 0% | 2019-10-27 | Swagger File - Dart & Instricutions | Low | Q4-19 | 2020-02-28 | Open API | Sergey |  | Grant Round Q419 | Open API Client & Documentation
To Do |  | 0% | 2019-10-27 | Swagger File - Kotlin & instructions | Low | Q4-19 | 2020-02-28 | Open API | Sergey |  | Grant Round Q419 | Open API Client & Documentation
To Do |  | 10% | 2019-10-27 | PEG Asset Explorer - R&D | Medium | Q4-19 |  | PegNet | Sergey | Mitchell | Community Project | Asset Explorer for PEGNET and eventually FAT/Factom
To Do | 0% | 0% | 2019-11-03 | Swagger File - Rust & instructions | Medium | Q4-19 | 2020-02-28 | Open API | Sergey |  |  | Open API Client & Documentation

## Sheet2
Status
To Do
Complete
In Progress